## General
Change Runbook
General Information
Change number (TOPdesk) | BW2606 4650
Epic/Feature/Story number (Jira)
Change short description | Migrating Internet (DC Network: 45.14.0.0/25) from Provide to Mikrotik
Application / Infrastructure | Network
Change Classification (result of CRIA) | Normal Major Change
Author name | Roland Peeters
Author phone | +31638190688
Version | 0.3
Implementation Date | Weekend
Implementation Start Time CE(S)T
Implementation End Time CE(S)T
Configuration Items involved
Sophos FW001
Sophos FW002
FortiGate 1800F-1
FortiGate 1800F-2
FortiGate 500E-1
FortiGate 500E-2
CPE10676 SW1
CPE10678 SW2
Cisco
Huawei
Mikrotik
Change & release manager Roland Peeters roland.peeters@boels.nl

## Impact
Impact
Affected Applications / Services
Application / Service | Affected | Impact | Risk Mitigating Actions | Remarks | Team informed
Abird
Active Directory
Autocad
Basware
CanopyDeploy
Coachview
Coupa
FleetWave
Hydra
IAM
InspHire
Manual Master
MuleSoft
Network |  | No internet connection for 15 min. Whole Boels Network. | Revert to old network in minutes
O-Prognose
Ortec
Outlook
OutSystems
Planon
Qlik sense
RPA
RTAG
Ruptela
SAP
Successfactors
VPN
WLP
<Fill in>
<Fill in>
<Fill in>
<Fill in>
<Fill in>
<Fill in>
<Fill in>
<Fill in>

## Communication
Communication
Involved Staff
Name | Role | Business Phone | Email Address | Department | Delete contact rows of not involved staff & add missing contacts
Roel Pluymen | Informative | +31611388111 | roel.pluijmen@boels.nl | IT Operations Infra
Roland Peeters | Informative | +31638190688 | roland.peeters@boels.nl | Change & Release Manager
Pieter Zeldenthuis | Realization | +31(0)884634772 | p.zeldenthuis@infopact.nl | Netwerk
Joop Marijne | Realization | +31(0)624112911 | joop.marijne@provide.nl | Netwerk
Axians | Realization | +31(0)8002255468 | axians@service-now.com | FortiNet
Support | Realization | +31(0)402902800 | support@aragorn.nl | Sophos
Clifton | Coordination | +31634747125 | clifton.dobbelsteyn@boels.nl | IT Operations Infra
ESCALATION
Name | Role | Business Phone | Email Address | Department | Do not delete contacts
Roel Pluymen | Escalation | +31611388111 | roel.pluijmen@boels.nl | Manager Infrastructure
Burak Uygur | Escalation | +46723310680 | burak.uygur@cramo.com | Incident Manager
Bob de Leeuw | Escalation | +31610375731 | bob.deleeuw@boels.nl | Director HQ ICT
Malin Karlstrand | Escalation | +46733434544 | malin.karlstrand@cramo.com | Head of IT Application Management
Toussin Pooters | Escalation | +31650565847 | toussin.pooters@boels.nl | Manager Change Office
Dave Lardinois | Escalation | +31624192945 | dave.lardinois@boels.nl | Manager Data & Integrations
Mikael Levén | Escalation | +46738096020 | mikael.leven@cramo.com | Head of Software Development
Richard Bolk | Escalation | +31651324671 | richard.bolk@boels.nl | Head of IT Operations

## Runbook
RUNBOOK
PRE IMPLEMENTATION
Activity | Activity description | Resource | Date dd-mmm-YY | Time hh:mm CE(S)T | Duration hh:mm | Comments |  | Status
1.01 | Voorbereiden bekabeling | Clifton, Roel, Frank | 2026-06-07 | 8:30 | 3:00 | Cabling installed, labeled, tested, and neatly dressed within the rack. |  | Completed
1.02 | Let Infopact configure their network ports | Infopact | 2026-06-07 | 11:30 | 0:03 | Confirmed by Infopact configuration is completed |  | Completed
1.03 | Test the new Internet | Clifton, Roel | 2026-06-07 | 11:33 | 0:03 | Roel confirmed all tests were succesfully |  | Completed
1.04 | Documentation | Clifton, Roel | 2026-06-15 | 11:36 | 46254 | Label management = done, racks&cables = done, |  | Completed
1.05 | Create Change & Runbook | Clifton, Roel | 2026-08-27 | 10:00 | 1:00 | CAB on 27-08-26 |  | In Progress
1.06 | Align all participants | Clifton, Roel | 2026-08-27 | 11:00 | 0:03 | After approval CAB |  | In Progress
1.07 | Arrange datacenter access in accordance with the agreed schedule. | Clifton, Roel | 2026-08-27 | 11:03 | 0:03 | After approval CAB |  | In Progress
1.08 | Coordinate with Provide on when they will stop advertising their network | Clifton, Roel | 2026-08-27 | 11:06 | 0:03 | Has to be simulanious with 2.02 |  | Completed
1.09 | Coordinate with Infopact on when they should start advertising their network | Clifton, Roel | 2026-08-27 | 11:09 | 0:03 | Has to be simulanious with 2.01 |  | Completed
1.1 | Inform and coordinate with Axians regarding the planned downtime of both Fortinet clusters (no configuration changes are required on their side) and schedule validation checks after the migration. | Clifton, Roel | 2026-08-27 | 11:12 | 0:03 | After approval CAB |  | Completed
1.11 | Plan a maximum 15-minute internet outage in the Boels datacenter for the migration. | Clifton, Roel | 2026-08-27 | 11:15 | 0:03 | After approval CAB |  | Planned
1.12 | Confirm resource availability | All Teams | 2026-08-27 | 11:18 | 46254 | Confirmation by e-mail |  | Completed
1.13 | Notify stakeholders & confirm change window | Change Manager | 2026-08-27 | 46254.4708 | 3:00 |  |  | Planned
IMPLEMENTATION
Activity | Activity description | Resource | Date dd-mmm-YY | Time hh:mm CE(S)T | Duration hh:mm | Service Downtime | Comments | Status
2.01 | Coordinate with Provide on when they will stop advertising their network | Clifton, Roel | 2026-09-05 | 22:00 | 0:00 | Yes |  | Planned
2.02 | Coordinate with Infopact on when they should start advertising their network | Clifton, Roel | 2026-09-05 | 22:00 | 0:00 | Yes |  | Planned
2.03 | Inform and coordinate with Axians regarding the planned downtime of both Fortinet clusters (no configuration changes are required on their side) and schedule validation checks after the migration. | Clifton, Roel | 2026-09-05 | 22:00 | 0:00 | Yes |  | Planned
2.04 | Inform and coordinate with Aragorn regarding the planned downtime of the Sophos cluster (no configuration changes are required on their side) and schedule validation checks after the migration. | Clifton, Roel | 2026-09-05 | 22:00 | 0:15 | Yes |  | Planned
2.05 | Move the physical cabling from the Cisco and Huawei devices to the Mikrotik switches | Clifton, Roel | 2026-09-05 | 22:15 | 00:05 | Yes |  | Planned
2.06 | Testing, see tabular testplan | Testers | 2026-09-05 | 22:20 | 0:40 | No |  | Planned
2.07 | Notify stakeholders change completed | Clifton, Roel | 2026-09-05 | 23:00 | 0:01 | No |  | Planned
2.08 | Go/NoGo | Clifton, Roel | 2026-09-05 | 23:01 | 0:01 | No | No Go = Fallback (see TAB FallBack plan)
2.09 |  |  |  | 23:02 | 00:05 | No | Go if succesfull | Planned
2.1 |  |  |  | 23:07 | 00:05 | No |  | Planned
POST IMPLEMENTATION
Activity | Activity description | Resource | Date dd-mmm-YY | Time hh:mm CE(S)T | Duration hh:mm | Comments |  | Status
4.01 | Process new situation in Drawing and documentation | E. de Jong, Roel, Clifton |  | 9:00 | 1:00 |  |  | Planned
4.02 |  |  |  | 10:00 | 0:05 |  |  | Planned

## Test plan
Test Plan
Test & Validation
Test Case nr | Test Case | Environment | Acceptance criteria | Resource | Date dd-mmm-YY | Duration hh:mm | Expected Result | Actual Result | Remarks
1 | Review validation check Axians |  | Axians |  |  |  | Acceptance Criteria: Axians confirms the Fortinet environment is healthy and operating normally. Expected Result: No critical alarms detected No HA issues detected All Fortinet services operational No abnormal traffic patterns observed No routing anomalies detected
2 | Review validation check Aragorn |  | Aragorn |  |  |  | Acceptance Criteria: Aragorn confirms the Sophos environment is healthy and operating normally. Expected Result: No critical Sophos alerts detected No abnormal CPU or memory utilisation All security policies active No unexpected security events generated
3 | Validate interface status |  | Clifton, Roel |  |  |  | Acceptance Criteria: All network interfaces involved in the migration are operational. Expected Result: WAN interfaces are Up/Up No interface errors No CRC errors No packet drops No interface flapping detected
4 | Verify routing table |  | Clifton, Roel |  |  |  | Acceptance Criteria: Traffic is routed through the new internet path. Expected Result: Default route points to Mikrotik Old Provide route no longer active Route preference configured correctly No unexpected static routes present
5 | Verify BGP status and route advertisements |  | Clifton, Roel |  |  |  | Acceptance Criteria: All BGP sessions are operational and stable. Expected Result: BGP session Established Required prefixes received Required prefixes advertised No route flapping No route dampening detected
6 | Validate internet connectivity |  | Clifton, Roel |  |  |  | Acceptance Criteria: Outbound internet connectivity is fully operational through the new Mikrotik internet connection and all critical external services remain accessible. Expected Result: Internet browsing operational HTTPS connectivity operational Microsoft 365 reachable No packet loss observed Acceptable latency levels Successful traceroute to external destinations Public IP address reflects the new internet provider Traffic is routed via the new internet path No unexpected routing behaviour detected Validation Targets: login.microsoftonline.com portal.azure.com outlook.office.com www.microsoft.com teams.microsoft.com
7 | Validate DNS functionality |  | Clifton, Roel |  |  |  | Acceptance Criteria: Internal and external DNS resolution operate correctly. Expected Result: Internal DNS records resolve successfully External DNS records resolve successfully No DNS timeout events DNS response times within normal range
8 | Check VPN (IKE/IPSec) status |  | Clifton, Roel |  |  |  | Acceptance Criteria: All required VPN services remain operational. Expected Result: All IPSec tunnels are Up No tunnel negotiation failures Expected traffic passing through tunnels No packet loss observed No tunnel flapping detected
9 | Business Service Validation |  | Clifton, Roel |  |  |  | Acceptance Criteria: Critical business applications remain operational following the migration. Expected Result: Microsoft 365 accessible Outlook operational Teams operational SAP operational No authentication issues No user-reported connectivity issues
10
Findings
Finding | Summary | Environment | Status | Detected by | Assigned to | Detected on Date | Business Impact | Prio | Solved on Date
1 | <Describe the Findings that are been discovered during the change. A finding can be an error, bug, defect etc. Anything that is unexpected behavior>
2
3
4
5
0

## Fallback plan
Fallback plan
Roll Back Activities
Activity | Activity description | Resource | Date * dd-mmm-YY | Time hh:mm CE(S)T | Duration hh:mm | Service Downtime | Comments | Status
4.01 | Coordinate with Infopact on when they will stop advertising their network | Clifton, Roel | 2026-09-05 | 23:00 | 0:00 | Yes
4.02 | Coordinate with Provide on when they should start advertising their network | Clifton, Roel | 2026-09-05 | 23:00 | 0:00 | Yes
4.03 | Inform and coordinate with Axians regarding the planned downtime of both Fortinet clusters (no configuration changes are required on their side) and schedule validation checks after the migration. | Clifton, Roel | 2026-09-05 | 23:00 | 0:00 | Yes
4.04 | Inform and coordinate with Aragorn regarding the planned downtime of the Sophos cluster (no configuration changes are required on their side) and schedule validation checks after the migration. | Clifton, Roel | 2026-09-05 | 23:00 | 0:15 | Yes
4.05 | Move the physical cabling from the Mikrotik switches to the Cisco and Huawei devices | Clifton, Roel | 2026-09-05 | 23:15 | 00:05 | Yes
4.06 | testing see testplan | All teams | 2026-09-05 | 23:20 | 00:06 | No
4.07
4.08
4.09
4.1
4.09
4.1
4.11 | Roll Back ¦ Go/NoGo | [5 empty] | No Go = Escalation, see communication TAB
4.12 | go/no go
4.13

## Data (hidden)
Data sheet
Application | Classification | Environment | Role | Status | Service Downtime | Status | Go/NoGo | Test | Priority | PSWD
inspHire | Normal Major Change | Development | Coordination | New | Yes | Planned | Go | PASS | CRITICAL | rp
Hydra | Normal Minor Change | Test | Standby | Investigation | No | In Progress | NoGo | FAIL | HIGH
OutSystems | Standard Change | QAS | Testing | Workaround given |  | Completed |  | See remarks | NORMAL
SAP | Emergency Change | Production | Realization | Resolved |  | Skipped |  |  | LOW
Infra | Epic |  | Escalation | Closed |  | On Hold
System Management | Feature |  | Disbale/Enable Service & Testing
Network | Story |  | Informative
Other