## General
GENERIC Change Runbook
General Information
Change number (TOPdesk) | BW2603 1081
Epic/Feature/Story number (Jira)
Change short description | Cramo SQL Update
Application / Infrastructure | Other
Change Classification (result of CRIA) | Normal Major Change
Author name | Roland Peeters
Author phone | +31638190688
Version | 0.2
TEST¦ Implementation Date CE(S)T | Completed
TEST¦ Implementation Start Time CE(S)T | Completed
TEST¦ Implementation End Time CE(S)T | Completed
PROD ¦ Implementation Date CE(S)T | 2026-09-23
PROD ¦Implementation Start Time CE(S)T | 17:30
PROD ¦ Implementation End Time CE(S)T
Configuration Items involved | SQLT01
SQLPROD01
SQLPROD02
Canea
Therefore
Handyman
Change & release manager Roland Peeters roland.peeters@boels.nl

## Impact
Impact
Affected Applications / Services
Application / Service | Affected | Impact | Risk Mitigating Actions | Remarks | Team informed
Abird
Active Directory
Autocad
Basware
CanopyDeploy
Coachview
Coupa
FleetWave
Hydra
IAM
InspHire
Manual Master
MuleSoft
Network
O-Prognose
Ortec
Outlook
OutSystems
Planon
Qlik sense
RPA
RTAG
Ruptela
SAP
Successfactors
VPN
WLP
Cramo Canea |  | Application not available | Roll back procedure in place & Testing is part of the change
Cramo Handyman |  | Application not available | Roll back procedure in place & Testing is part of the change
Ctamo Therefore |  | Application not available | Roll back procedure in place & Testing is part of the change
<Fill in>
<Fill in>
<Fill in>
<Fill in>

## Communication
Communication
Involved Staff
Name | Role | Business Phone | Email Address | Department | Delete contact rows of not involved staff & add missing contacts
Roel Pluymen |  | +31611388111 | roel.pluijmen@boels.nl | IT Operations Infra
Roland Peeters |  | +31638190688 | roland.peeters@boels.nl | Change & Release Manager
Emile Coenen |  | +31611388096 | emile.coenen@boels.nl | ERP InspHire
CGI Infra Team
B3
Shibuya
ESCALATION
Name | Role | Business Phone | Email Address | Department | Do not delete contacts
Roel Pluymen | Escalation | +31611388111 | roel.pluijmen@boels.nl | Manager Infrastructure
Bob de Leeuw | Escalation | +31610375731 | bob.deleeuw@boels.nl | Director HQ ICT
Toussin Pooters | Escalation | +31650565847 | toussin.pooters@boels.nl | Manager Change Office
Dave Lardinois | Escalation | +31624192945 | dave.lardinois@boels.nl | Manager Data & Integrations
Richard Bolk | Escalation | +31651324671 | richard.bolk@boels.nl | Head of IT Operations

## Runbook - PROD
PROD RUNBOOK ¦ SQLPRD01 & SQLPRD02
PRE IMPLEMENTATION
Activity | Activity description | Resource | Date dd-mmm-YY | Time hh:mm CE(S)T | Duration hh:mm | Comments |  | Status
1.01 | Arrange required resources for installation & testing | CGI Infra Team | [5 empty] | In Progress
1.02 | CAB Approval PROD | CAB | [5 empty] | Planned
1.03 | Communicate unavailability to stakeholders | Change & Releas mgr | [5 empty] | Planned
1.04 | Schedule an Installation & Test meeting with all involved resources | CGI Infra Team | [5 empty] | Planned
IMPLEMENTATION
Activity | Activity description | Resource | Date dd-mmm-YY | Time hh:mm CE(S)T | Duration hh:mm | Service Downtime | Comments | Status
2.01 | Ensure all fallback requirements (backup, save configuration, etc) have been met and check if relevant if monitoring is disabled. | B3/Shibuya | 2026-09-23 | 17:30 | 0:05 | No |  | Planned
2.02 | Perform health checks: a. Disks b. Services c. Event logs | CGI Infra Team | 2026-09-23 | 17:35 | 0:05 | No |  | Planned
2.03 | Create Snapshots SQLPROD01, SQLPROD02 | Shibuya | 2026-09-23 | 17:40 | 0:15 | Yes |  | Planned
2.04 | Identify the primary (active) server within the SQL Always On cluster. | B3 | 2026-09-23 | 17:55 | 0:03 | Yes |  | Planned
2.05 | Establish a remote desktop session to the secondary (passive) server in the SQL Always On cluster. | B3 | 2026-09-23 | 17:58 | 0:03 | Yes |  | Planned
2.06 | Verify the availability of recent backups for system databases. If necessary, create new backups. | B3 | 2026-09-23 | 18:01 | 0:10 | Yes |  | Planned
2.07 | Execute the SQL Server update on the secondary server by running the installation file as an administrator. | B3 | 2026-09-23 | 18:11 | 0:30 | Yes |  | Planned
2.08 | Restart the server upon completion of the update. | CGI Infra Team | 2026-09-23 | 18:41 | 0:15 | Yes |  | Planned
2.09 | Log into the server and confirm that SQL Server services are operational. Additionally, review Windows Server system and application logs, Disks and Services. | CGI Infra Team | 2026-09-23 | 18:56 | 0:10 | Yes |  | Planned
2.1 | Connect via SSMS from an administrative server (jump server) to the updated server. Inspect database status, job execution status, and SQL Server Error Log. | B3 | 2026-09-23 | 19:06 | 0:10 | Yes |  | Planned
2.11 | If all system checks are successful, verify SQL Server Always On synchronization status. If synchronization is intact, proceed with failover of the SQL Always On Availability Group (AG) to the updated server. | B3 | 2026-09-23 | 19:16 | 0:10 | Yes |  | Planned
2.12 | Start testing | CGI Infra Team | 2026-09-23 | 19:26 | 0:05 | No |  | Planned
2.13 | Start Testing see tabular " Testplan - PROD" |  | 2026-09-23 | 19:31 | 1:00 | No |  | Planned
2.14 | Testing ¦ Go/NoGo | CGI Infra Team | 2026-09-23 | 20:31 | 0:05 | No | No Go = Fallback (see TAB FallBack plan - PROD) | Planned
2.15 | Update the other SQL Server node. | B3 | 2026-09-23 | 20:36 | 0:30 | No |  | Planned
2.16 | Restart the server upon completion of the update. Infra | CGI Infra Team | 2026-09-23 | 21:06 | 0:15 | No |  | Planned
2.17 | Log into the server and confirm that SQL Server services are operational. Additionally, review Windows Server system and application logs. | CGI Infra Team | 2026-09-23 | 21:21 | 0:10 | No |  | Planned
2.18 | Connect via SSMS from an administrative server (jump server) to the updated server. Inspect database status, job execution status, and SQL Server Error Log. | B3 | 2026-09-23 | 21:31 | 0:10 | No |  | Planned
2.19 | 14. If all system checks are successful, verify SQL Server Always On synchronization status. If synchronization is intact, proceed with failover of the SQL Always On Availability Group (AG) to the updated server. | B3 | 2026-09-23 | 21:41 | 0:10 | No |  | Planned
2.2 | PROD ¦ FINAL Go/NoGo | CGI Infra Team | 2026-09-23 | 21:51 | 0:05 | No | No Go = Fallback (see TAB FallBack plan - TEST)
2.21 | Communicate Result | CGI Infra Team | 2026-09-23 | 21:56 | 0:05 | No | Communicate result to stakeholders | Planned
POST IMPLEMENTATION
Activity | Activity description | Resource | Date dd-mmm-YY | Time hh:mm CE(S)T | Duration hh:mm | Comments |  | Status
3.01 | Enable monitoring if it has been disabled in previous activities. Attach all required Change Evidence to the ticket. | B3 / CGI Infra Team/Shibuya | 2026-09-23 | 22:01 | 0:10 |  |  | Planned
3.02 | [7 empty] | Planned
3.03 | [7 empty] | Planned
3.04 | [7 empty] | Planned

## Test plan - PROD
Test Plan ¦ PROD
Test & Validation
Test Case nr | Test Case | Environment | Acceptance criteria | Resource | Date dd-mmm-YY | Duration hh:mm | Expected Result | Actual Result | Remarks
Canea
Canea-1 | Logging in to WoW. Checking that this is OK | Production | No issues | Jeannette/Kjetil | 2026-09-23 | 0.0069444 | No issues
Canea-2 | Starting Admin in WoW. Checking if possibility to add/ change users is OK | Production | No issues | Jeannette/Kjetil | 2026-09-23 | 0.0069444 | No issues
Canea-3 | Starting Design in WoW. Checking if possibility to chang register is OK | Production | No issues | Jeannette/Kjetil | 2026-09-23 | 0.0069444 | No issues
Canea-4 | Create a few cases to check that the workflow is OK | Production | No issues | Jeannette/Kjetil | 2026-09-23 | 0.0069444 | No issues
Canea-5 | Check your category content exists in Navigator. | Production | No issues | Jeannette/Kjetil | 2026-09-23 | 0.0069444 | No issues
Canea-6 | Check that it is possible to start WoW from the phone | Production | No issues | Jeannette/Kjetil | 2026-09-23 | 0.0069444 | No issues
Handyman
Handyman-1 | Log in to Handyman Office. | Production | No issues | Namita | 2026-09-23 | 0.0034722 | No issues
Handyman-2 | Log in to Handyman Mobile. | Production | No issues | Namita | 2026-09-23 | 0.0034722 | No issues
Handyman-3 | Create new Handyman order. Check integration to Rental works normally. | Production | No issues | Namita | 2026-09-23 | 0.010417 | No issues
Handyman-4 | Create new Rental order. Check integration from Rental to Handyman and back works normally. | Production | No issues | Namita | 2026-09-23 | 0.010417 | No issues
Handyman-5 | Create new Handyman order. Check integration to Therefore works normally. | Production | No issues | Namita | 2026-09-23 | 0.010417 | No issues
Handyman-6 | Create new Handyman job report. Check integration to Therefore works normally; Order summary, attachnments, checklist are moved to Therefore and can be viewed. | Production | No issues | Namita | 2026-09-23 | 0.010417 | No issues
Therefore
Therefore-1 | Create new Rental order. Check integration to Therefore works normally. | Production | No issues | TBD | 2026-09-23 | 0.0034722 | No issues
Therefore-2 | Create new Handyman order. Check integration to Therefore works normally. | Production | No issues | TBD | 2026-09-23 | 0.010417 | No issues
Therefore-3 | Create new Handyman job report. Check integration to Therefore works normally. | Production | No issues | TBD | 2026-09-23 | 0.010417 | No issues
Content and features
Therefore-5 | Check your categories exist in Navigator. | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-6 | Check your category content exists in Navigator. | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-7 | Security settings remain correct | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-8 | Favourites exist | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Office Add-Ins
Therefore-9 | Check Office add-ins exist (Excel, Word, PowerPoint, Outlook) | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore Navigator
Therefore-10 | Free text search | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-11 | Hit List search | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-12 | Open a document in Therefore Viewer - .pdf | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-13 | Version history exists in document | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-14 | Edit document in Therefore Viewer - ,pdf | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-15 | Editing index data | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-16 | Export documents from Therefore - Export to local disk | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-17 | Export documents from Therefore - Convert files to pdf | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-18 | Send documents from Therefore - Email original document | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-19 | Send documents from Therefore - Email , convert document tp pdf | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-20 | Send documents from Therefore - Email link to document in web-access | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-21 | Print files, Therefore Viewer | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-22 | Create new document - Therefore Navigator; New Document | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-23 | Create new document - Therefore Navigator; Drag and Drop | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-24 | Add to existing document - Therefore Viewer; Add files | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-25 | Add to existing document - Therefore Viewer; Drag and Drop | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-26 | Remove document - Therefore Navigator; Delete | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Web-access
Therefore-27 | Log in to Therefore Web-access | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-28 | Viewer shows documents | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-29 | Excel opens for viewing | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-30 | Version history exists | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-31 | New WebClient opens to viewing | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Solution Designer
Therefore-32 | Workflows exist | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-33 | Keyword dictionaries exist | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Therefore-34 | Security settings remain correct | Production | No issues | TBD | 2026-09-23 | 0.00069444 | No issues
Findings
Finding | Summary | Environment | Status | Detected by | Assigned to | Detected on Date | Business Impact | Prio | Solved on Date
1 | <Describe the Findings that are been discovered during the change. A finding can be an error, bug, defect etc. Anything that is unexpected behavior>
2
3
4
5
6
7
8
9
10

## Fallback plan - PROD
Fallback plan TEST ¦ SQLTEST1
Roll Back Activities
Activity | Activity description | Resource | Date * dd-mmm-YY | Time hh:mm CE(S)T | Duration hh:mm | Service Downtime | Comments | Status
Roll back activities after a NoGo DEV or QAS
4.01 | Uninstall the service pack (SP) and cumulative update (CU) for SQL Server | B3 | 2026-09-23 | 21:51 | 0:30 | Yes | Via Control Panel > Programs > Programs and Features > Installed Updates.
4.02 | Roll Back TEST ¦ Go/NoGo | CGI Infra Team | 2026-09-23 | 22:21 | 0:05 | No | No Go = Continue with 4.03
4.03 | Restore system databases and user databases from the most recent backup taken prior to the update. | B3 | 2026-09-23 | 22:26 | 1:00 | Yes
4.04 | Roll Back TEST ¦ Go/NoGo | CGI Infra Team | 2026-09-23 | 23:26 | 0:05 | No | No Go = Escalation, see communication TAB
4.05 | Communicate Result | CGI Infra Team | 2026-09-23 | 23:31 | 0:05 | No | Communicate result to stakeholders
4.06 | Enable monitoring if it has been disabled in previous activities. | Shibuya | 2026-09-23 | 23:36 | 0:05 | No

## Data (hidden)
Data sheet
PSWD
Application | Classification | Environment | Role | Status | Service Downtime | Status | Go/NoGo | Test | Priority | rp
inspHire | Normal Major Change | Development | Coordination | New | Yes | Planned | Go | PASS | CRITICAL
Hydra | Normal Minor Change | Test | Standby | Investigation | No | In Progress | NoGo | FAIL | HIGH
OutSystems | Standard Change | QAS | Testing | Workaround given |  | Completed |  | See remarks | NORMAL
SAP | Emergency Change | Production | Realization | Resolved |  | Skipped |  |  | LOW
Infra | Epic |  | Escalation | Closed |  | On Hold
System Management | Feature |  | Disbale/Enable Service & Testing |  |  | On Hold
Network | Story |  | Informative
Other